Responsibilities delegated to the Chief Investigator for CTIMP Trials Sponsored by NHS Greater Glasgow & Clyde

Study Title:

EudraCT No.:

Chief Investigator:

Under the co-sponsorship arrangement, the Chief Investigator is required to: (From decision to sponsor until R&I approval)

- Attend a risk assessment meeting with Sponsor representatives and other TMG members to discuss the risks involved in the study and how these can be mitigated.

- Ensure that he/she and all the research team know the principles of GCP and have received appropriate trial-specific and GCP training.

- Ensure his/her research team have the necessary resources, expertise, experience and education to perform their roles to the required standards.

- Ensure that the CI section of the Trial Master File (TMF) is created, held and updated in accordance with the requirements outlined by the Sponsor.

- Working with Sponsor Reps, ensure that Ethical approval, MHRA approval and local permissions/approvals are in place before recruitment begins.

(During the Trial)

- Ensure all Glasgow Health Science Partnership Board (GHSP Board) and Clinical Trial-specific SOPs and guidance, identified as relevant to the CI and/or study are adhered to throughout the life of the project.

- Confirm, as specified in the site agreement an up to date Trial-specific training log of all personnel selected for and trained to work on the trial and ensure that their delegated duties are recorded and kept up to date in a trial delegation log.

- Confirm, as delegated to the study Project Manager, all new staff are provided with trial-appropriate training and details of this are recorded in the study site file.

- Ensure that consent is given freely and in writing from all subjects or the subject’s legal representative before they are involved in any trial procedures.

- Ensure all Trial-related medical decisions are made by an appropriately qualified healthcare professional.

- Ensure that Case Report Forms are completed accurately and that adverse events are recorded fully. Any corrections on this documentation must adhere to good document management practice.

- Ensure that all data are collected, used and stored in accordance with the Data Protection Act (2018) and are compliant with GDPR.

- Ensuring trial procedures for reporting SAE and SUSARs are followed within the time frames required by law and as outlined in the protocol.

- Ensure all proposed amendments to the trial protocol are discussed, reviewed and approved by Sponsors before being submitted to REC and MHRA (and any other relevant committees). All relevant amendment approval/permissions should be received prior to amendment implementation.

- Ensure that the University are kept informed of any amendments to the protocol so that adequate insurance can be maintained throughout the trial duration.

- Ensure that all potential trial sites are discussed with the TMG so that appropriate contractual arrangements can be put in place.

- Ensure that the REC and MHRA is informed of all new trial sites.

- Submit an annual progress and annual safety report to the sponsor, the REC and MHRA 12 months after the date on which favourable opinion was given and ensure that the reports are submitted thereafter until the end of the study.

(During close-down)

- Notify the MHRA and the REC of the end of the trial within 90 days if the trial runs to the planned completion date and within 15 days if stopped prematurely.

- Must provide a summary of the trial to the main REC and MHRA within 1 year of the end of the trial.

- Must ensure that trial records are archived in accordance with the protocol.

- Ensure that EudraCT database is updated with study results.

(Throughout the course of the trial and until records are destroyed)

- Allow access to the CI and Site Files and all trial-associated documents to Auditors and Monitors on request.

- Facilitate Statutory inspections by assisting with the audit of TMF and trial-associated documentation.

By signing this document you confirm that you understand your obligations and that you will carry them out to the required standards. This includes following the list of sponsor-defined CI Standard Operating Procedures (please see below list of current CI SOPs) available on the Glasgow CTU website: https://www.glasgowctu.org/Home/sops/

# CI Signature: ________________________________________ # Name (PRINTED): ________________________________________ # Date: ________________________________________

Sponsor Defined CI Operating Procedures

| Number | Title |
| --- | --- |
| SOP 50.001 | NHS Greater Glasgow & Clyde Policies |
| SOP 50.013 | Setup and maintenance of training files: NHS |
| SOP 50.017 | Clinical Research & Development Document Management |
| SOP 50.019 | Independent Stakeholder Assessment (Glasgow Clinical Trials Unit) |
| SOP 50.020 | eCRF User Acceptance Testing (Glasgow Clinical Trials Unit) |
| SOP 51.001 | Protocol Development |
| SOP 51.002 | Participant Information Sheet and Consent Forms: Design and Approval |
| SOP 51.004 | Risk Assessment |
| SOP 51.007 | Identifying a Sponsor organisation |
| SOP 51.008 | Handling non-compliance with Good Clinical Practice (GCP) and/or the trial protocol in clinical research sponsored, co-sponsored or hosted by NHS Greater Glasgow and Clyde |
| SOP 51.009 | Notification of serious breaches of Good Clinical Practice or the trial protocol for clinical trials of investigational medicinal products |
| SOP 51.014 | Preparation and submission of IRAS forms |
| SOP 51.016 | Preparation and maintenance of a Trial Master File |
| SOP 51.017 | Registration of research projects on public databases |
| SOP 51.018 | Sponsor Oversight Checklist |
| SOP 51.019 | Sponsor – End of study procedures |
| SOP 51.020 | Sponsor Regulatory Green Light |
| SOP 51.021 | Sponsor Review and Approval of Amendments |
| SOP 51.023 | Sponsor process for an IDMC |
| SOP 51.024 | Archiving Essential Documents from Clinical Research – Process for a Sponsored Clinical Trial of an Investigational Medicinal Product (CTIMP) |
| SOP 51.025 | Archiving Essential Documents from Clinical Research – Process for a Sponsored Non CTIMP |
| SOP 51.028 | NHS Laboratory samples for Trials involving an Investigative Medicinal Compound (CTIMP) Sponsored by NHS GG&C or Co-sponsored by NHS GG&C and the University of Glasgow |
| SOP 51.029 | Writing Study Specific Laboratory Manuals for Trials involving Investigational Medicinal Products sponsored by NHS GG&C or Co-sponsored by NHS GG&C and the University of Glasgow |
| SOP 51.030 | Writing Sample Handling Manuals for Sites Participating in Clinical Trials of an Investigative Medicinal Product (CTIMP) Sponsored by NHS GG&C or Co-sponsored by NHS GG&C and University of Glasgow |
| SOP 51.033 | Research Imaging for Trials involving an Investigative Medicinal Compound (CTIMP) Sponsored by NHS GG&C or Co-sponsored by NHS GG&C and the University of Glasgow (UoG) |
| SOP 51.034 | Writing a Trial Specific Research Imaging Manual for Sites Participating in Clinical Trials of an Investigative Medicinal Product (CTIMP) Sponsored by NHS GG&C or Co-sponsored by NHS GG&C and University of Glasgow (UoG) |
| SOP 51.036 | Trial Steering Committee for Trials involving an Investigative Medicinal Compound (CTIMP) Sponsored by NHS GG&C or Co-sponsored by NHS GG&C and the University of Glasgow |
| SOP 52.014 | Archiving Essential Documents from Clinical Research – Process for Hosted Research |
| SOP 53.001 | Handling urgent safety measures for clinical trials for investigational medicinal products |
| SOP 53.002 | The Handling of Poor Quality and Fraud in Clinical Research |
| SOP 53.003 | Temporary halt or early termination of clinical trials of investigational medicinal products |
| SOP 53.004 | Monitoring Clinical Trials |
| SOP 55.001 | Pharmacovigilance in Clinical Trials of Investigational Medicinal Products (Glasgow Clinical Trials Unit) |
| SOP 55.002 | Preparation and submission of the Development Safety Update Report (Glasgow Clinical Trials Unit) |
| SOP 55.004 | Safety Reporting Requirements for Research Other Than Clinical Trials of Investigational Medicinal Products |
| SOP 55.006 | Management of IBs and SmPCs in CTIMPS |
| SOP 55.007 | Safety Reporting Requirements in Medical Device Trials and Studies |
| SOP 55.015 | Sponsor Pharmacovigilance Data |
| SOP 56.001 | Site Set up - Green for Go Process |
| SOP 56.007 | Project Management Site Capability Assessment |
| SOP 58.006 | Reporting Incidental Research Imaging Findings (Identifiable Images) |
| SOP 58.007 | CRIF Review of Incidental Findings (anonymised images) |